## Sheet1
|  |  | Task | Wed (during class) | Wed (During class) | Thu -Fri | Thu -Fri | Thu -Fri | Sat (during class) | Sat (during class) | Sun-Wed | Sun-Wed | Sun-Wed | Fri | Sat
Team Member | Roles | Skill | By OED on | 2019-06-26 | 2019-06-26 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-29 | 2019-06-29 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-05 | 2019-07-06
| All | Admin | create folder structure to function with the app
| Role1 | Admin | Decide data needed for Country Graph 1
| Role2 | Admin | Decide data needed for country Graph 2
| Role3 | HTML | Create index.html
| Role3 | HTML | create a div to contain drop down menu. (build code to pass to java)
| Role3 | HTML | Create div to contain chart#1
| Role3 | HTML | create div to contain chart #2
| Role3 | HTML | Create div to contain chart #3
| Role3 | HTML | beautify website (CSS, etc.)
| Role4 | Data | Create 3 different dataframe for chart1 we need country ranks by year. (top 10)
| Role4 | Data | Create 3 different data frames for chart2 data is yet to be decided, suggestions: cross walk between year winner and basic stats about the winner country.
| Role4 | Data | Create 3 different data frames for chart3 data is yet to be decided, suggestions: cross walk between year winner and basic stats about the winner country's players.
| Role4 | Data | Create 3 sql tables (one for each dataframe)
| Role4 | Data | Create a .SQLite file with the 3 database tables.
| Role4 | Data | Save .SQLite file in folder called DB
Erick | Role5 | Python/SQL alchemy | create python flask app.py (Use the bellybutton assignment as a template)
| Role5 | Python/SQL alchemy | reflect the 3 .SQLite database tables
| Role5 | Python/SQL alchemy | create home route to render index.html
| Role5 | Python/SQL alchemy | create route1 to return jasonified data--top 10 countries by world cup year.
| Role5 | Python/SQL alchemy | create route2 to return jasonified data--Country basic stats (as needed for country chart 2)
| Role5 | Python/SQL alchemy | create route3 to return jasonified data --Country/player's basic stats (as needed for country chart 3)
| Role5 | Python/SQL alchemy | create route4 to return jasonified data --year/winner for dropdown
| Role5 | Python/SQL alchemy | Save app.py under folder the root folder directory
| Role5 | Java Script | create app.js
| Role1 | Java Script | Chart #1: create code to insert chart#1 in built-in div for Chart#1 (use static data until the code works properly)
| Role1 | Java Script | Chart #1: create a function that grabs the data returned by reoute1 and creates the chart with the returned data
| Role2 | Java Script | Chart #2: create code to insert chart#2 in built-in div for Chart#2 (use static data until the code works properly)
| Role2 | Java Script | Chart #2: create a function that grabs the data returned by reoute2 and creates the chart with the returned data
| Role 4 | Java Script | Chart #3: create code to insert chart#3 in built-in div for Chart#3 (use static data until the code works properly)
| Role 4 | Java Script | Chart #3: create a function that grabs the data returned by route3 and creates the chart with the returned data
| Role 1 &2 | Java Script | Create Initialize function . Initialize should:
| Role 1 &2 | Java Script | update dropdown menu with route4
| Role 1 &2 | Java Script | create the graphs with some default data.
| Role 1 &2 | Java Script | Get new data when the dropdown changes, and execute the functions that create the graphs.
| Role 5 | Heroku | Deploy to Heroku
Presentation